## TIMELINE
Stages | Description | People | Plan Start | Plan End | Duration | Progress | April |  | Mei
[7 empty] | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Research Project (UART Interface) | All Division | 30/4/2019 | 2019-01-05 | 2 Days | 40% | bar: April 30 to Mei 1
| Decide what we want to buy | Sutopo | 30/4/2019 | 30/4/2019 | 1 Day | 60% | bar: April 30
1. USB to TTL converter | bar: April 30
| Try the program transmitter | Transmitter Division | 30/4/2019 | 2019-02-05 | 3 Days | 0% | bar: April 30 to Mei 2
| Try the program reciever | Reciever Division | 30/4/2019 | 2019-02-05 | 3 Days | 0% | bar: April 30 to Mei 2
| Assemble the circuit | Hardware Division | 2019-05-03 | 2019-03-05 | 1 Day | 0% | bar: Mei 3
2 | Try transmitter program with circuit | Transmitter Division | 2019-06-05 | 2019-07-05 | 2 Days | 0% | bar: Mei 6 to Mei 7
| Try reciever program with circuit | Reciever Division | 2019-06-05 | 2019-07-05 | 2 Days | 0% | bar: Mei 6 to Mei 7
| Try to combine the program with circuit | Reciever n Transmitter Div | 2019-08-05 | 2019-08-05 | 1 Day | 0% | bar: Mei 8
3 | Improvement project | All Division | 2019-08-05 | 2019-10-05 | 3 Days | 0% | bar: Mei 8 to Mei 10
| Prepare Poster | Sutopo | 2019-08-05 | 20/5/2019 | 3 Days | 0% | bar: Mei 8 to Mei 10
| Check project | All Division | 13/5/2019 | 17/5/2019 | 5 Days | 0% | bar: Mei 13 to Mei 17
| Ready for presentation | All Division | 20/5/2019 | 24/5/2019 | 5 Days | 0% | bar: Mei 20 to Mei 24

## BUDGET
Date | Notes | Debit | Kredit | Total
Total